ANNEX II: TERMS OF REFERENCE

Preparation, printing, producing, copying, distributing of promo materials

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	2

2.	OBJECTIVES & EXPECTED OUTPUTS	2

2.1.	Overall objective	2

2.2.	 Specific Objective(s)	3

2.3.	Expected outputs to be achieved by the contractor	3

3.	ASSUMPTIONS & RISKS	3

3.1.	Assumptions underlying the project	3

3.2.	Risks	3

4.	SCOPE OF THE WORK	3

4.1.	General	3

4.2.	Specific work	4

4.3.	Project management	4

5.	LOGISTICS AND TIMING	4

5.1.	Location	4

5.2.	Start date & period of implementation of tasks	4

6.	REQUIREMENTS	5

6.1.	Staff	5

6.2.	Office accommodation	7

6.3.	Facilities to be provided by the contractor	7

6.4.	Equipment	7

7.	REPORTS	7

7.1.	Reporting requirements	7

7.2.	Submission and approval of reports	8

8.	MONITORING AND EVALUATION	8

8.1.	Definition of indicators	8

8.2.	Special requirements	8

# BACKGROUND INFORMATION

## Partner country

## The Republic of Serbia

## Contracting authority

The Managing Authority for IPARD Programme (hereinafter: IPARD MA),

Department for Management of IPARD Programme

Ministry of Agriculture, Forestry and Water Management of the Republic of Serbia (hereinafter: MAFWM).

## Country background

The Republic of Serbia is located at the crossroads of Central and Southeast Europe and is the central part of the Balkans, spreading over an area of 77,589 km2. Its population is 6,945,235 of which 1,694,056 are living in Belgrade. According to OECD definition of rural areas in the Republic of Serbia it accounts for 79.5% of the country’s territory, encompassing about half of the total population (58.7%). The Republic of Serbia is actively pursuing the agenda of accession to the European Union.

In that respect the European Council granted the Republic of Serbia the status of a candidate country on 1st March 2012. The European Commission allocated for the Republic of Serbia the amount of EUR 175 million, within the Instrument for Pre-Accession Assistance (hereinafter: IPA) to be withdrawn by 2023 for rural development / IPARD. The IPARD II Programme was officially approved by the European Commission on 20th January 2015 by the Decision of the EC C (2015) 257 (the last modification – Decision of the EC AN/KF/D (2019) 4484892 dated 27 Jun 2019).

The adopted IPARD II Programme prescribes entrustment of six measures in three phases. By entry into force of the Financing Agreement between the Republic of Serbia and the European Commission on 12th June 2018, entrustment of budget implementation tasks was regulated for IPARD measures: 1 - Investments in physical assets of agricultural holdings and 3 - Investments in physical assets concerning processing and marketing of agriculture and fishery products. The Amendment to the Financing Agreement between the Republic of Serbia and the European Commission entered into the force on 17th November 2020, by which implementation of IPARD measures: 7 (Farm diversification and business development) and 9 (Technical Assistance) are enabled. From the beginning of the IPARD II Programme implementation so far 14 public calls have been announced and closed.

## Current situation in the sector

The Republic of Serbia has prepared the IPARD Programme for the period 2021-2027 (IPARD III Programme), approved by EC in March 2022. Seven measures are elaborated in IPARD III Programme and rollover is carried out for the same four IPARD II measures that were entrusted.

The visibility and promotional actions on IPARD Programme is obligation set in Article 24 of Framework agreement between the Republic of Serbia and the European Commission on the arrangements for implementation of Union financial assistance to the Republic of Serbia under the Instrument for pre-accession assistance (IPA II) and Article 30 of the Sectoral agreement between the Government of the Republic of Serbia and the European Commission setting out provisions for the management and implementation of Union financial assistance to the Republic of Serbia under the Instrument for pre-accession assistance in the policy area 'agriculture and rural development' (IPARD). During the last period visibility and promotional activities were financed from national budget and within different IPA and bilateral projects.

In regard to all above mentioned as well as to increase access to updated information about the IPARD Programme in the Republic of Serbia to all potential recipients following principles of transparency and equal treatment, IPARD MA needs the service of preparation, printing, producing, copying, distributing of promo materials.

## Related programmes and other donor activities

In regard to inform, present and promote pre-accession EU aid and funds, several projects were implemented.

The IPA 2013 project “Support to IPARD Operating structure (MA, IPARD Agency and Advisory services)”

The contract has been signed in June 2017. Implementation process started at the beginning of September 2017 with planned duration up to August 2019. Request for the extension of the project was accepted and the project was extended until the end of the 2019. The main results achieved by this project were support during accreditation of the first two IPARD II measures (1 and 3), the preparation of the entrustment package for IPARD II measures 7 (Farm diversification and business development) and 9 (Technical Assistance), as well as development of the RD IT solution.

Support of Government of Japan related to the promotional activities of IPARD II Programme and public calls. Within this support, Guides for IPARD recipients for Measures 1, 3 and 7 were prepared and printed, four TV spots were produced and broadcasted during public calls for Measures 1, 3 and 7.

FWC - Support to IPARD Managing Authority and IPARD Agency with the implementation of IPARD measures (Specific contract 2018-596) (2020 -2021) - Support to MA during the initial phase of the implementation IPARD II measures 7 and 9 through on the job support was related to the preparation of the Draft Rulebook on Technical Assistance measure (M9). Simulation training for relevant staff of the MA and IPARD Agency (IA) was delivered, five TDs were prepared. Four Modules focused on the different topics related to preparation of tender and contract dossiers, ex-ante control, tender dossier evaluation and monitoring the implementation of the relevant contracts (service or supply) were held. The materials for the IPARD III programme were prepared in accordance with the deadlines set by the EC including remaining chapters. Stakeholder consultations on the IPARD III programme are published on the website as well as the questionnaire for suggestions and comments. The Training programme for M6 was prepared and a two-part workshop was held for MA and IA staff. IPARD Agency staff was prepared to implement IPARD II measures 7 and 9 in line with EU requirements. Existing RD IT solution for the implementation of IPARD II programme was upgraded.

The IPA 2017 project “Support to IPARD Operating structure (Managing Authority, IPARD Agency)” (finished in March 2023) - The activities related to the preparation of procedures for the rollover of investment measures to the IPARD III Programme were successfully performed and mature drafts of rulebooks and supporting documents were developed. Workshops on the implementation of investment measures were conducted to discuss the open issues and improve the drafted documents. During the project, the development of procedures for the entrustment of measures 4 and 5 started and drafts of rulebooks and supporting documents were produced. Eight workshops for both measures were held to obtain a better understanding about the measures’ specificities and improve the developed drafts of documents. Study visits to Slovenia and Croatia were arranged and conducted in order to research the good practices from the implementation of measure 4 and measure 5.

# OBJECTIVES & EXPECTED OUTPUTS

## Overall objective

The overall objective (Impact) is more efficient and effective implementation of the IPARD Programme by informing the general public about opportunities of EU assistance for agriculture and rural development to the Republic of Serbia and increasing number of potential recipients and recipients of the IPARD Programme.

## Specific objective(s)

The specific objectives (Outcomes) of this contract are as follows:

Outcome 1: to increase access to updated information about the IPARD Programme in the Republic of Serbia to potential recipients and recipients of IPARD measures 1,3,4,5 and 7 through service for preparation, printing, producing, copying, distributing of guides for applicants.

Outcome 2: to inform the general public, stakeholders, potential IPARD recipients and IPARD recipients, the IPARD structures and related bodies, potential Local Action Groups (pLAG’s) and National Rural (Development) Network, about IPARD opportunities and overall support provided from EU to the Republic of Serbia for agriculture and rural development through service for preparation, printing, producing, copying, distributing of printed materials of IPARD measures 1,3,4,5 and 7 for applicants.

## Expected outputs to be achieved by the contractor

The expected outputs of this contract are as follows:

Output 1: Prepared, printed, produced, copied, distributed guides for IPARD measures 1,3,4,5 and 7 (outcome1);

Output 2: Prepared, printed, produced, copied, distributed leaflets for IPARD measures 1,3 and 7 (outcome 2);

Output 3: Prepared, printed, produced, copied, distributed brochures for IPARD measures 1 and 3 (outcome 2);

Output 4: Printed/copied material for MC meetings (outcome 2);

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

- The staffing level of beneficiary institution is adequate for the successful implementation of the activities. Activities are timely and effectively implemented.

- The MA staff is providing the content for the printed promotional material to the Contractor in timely manner as well as approving of design proposals of printed promo material.

## Risks

- Insufficient availability and staffing of beneficiary institution to actively and effectively participate in the implementation of the project.

- Delay in providing of the content and/or approval of design proposals of the printed promotional material.

# SCOPE OF THE WORK

## General

The promotional material is intended to increase access to updated information about the IPARD Programme in the Republic of Serbia to potential recipients and recipients of IPARD measures 1,3,4,5 and 7 as well as to inform the general public, stakeholders, potential IPARD recipients and IPARD recipients, the IPARD structures and related bodies, potential Local Action Groups (pLAG’s) and National Rural (Development) Network, about IPARD opportunities and overall support provided from EU to the Republic of Serbia for agriculture and rural development through service for preparation, printing, producing, copying, distributing promotional material.

The general scope of work is preparation (including design), printing, producing, copying, distributing of promo materials (brochures, leaflets and guides).

Upon Contract expiry date, the IPARD Managing Authority requires a fully designed and printed promo material.

### Description of the assignment

### Preparation, printing, production, copying, distribution of promotional material will take place in stages that will provide printed promotional material in accordance with the requirements of the contracting authority. In performing the task, the Contractor should ensure that the following conditions are met:

| IPARD Guides |  |
| --- | --- |
| Dimensions/format | 165x235mm |
| Cover page | 300g-350g/m2 fine art paper (kunstdruk), matte lamination 1/0 |
| Inner paper | Paper, 135-150g/m2 |
| Number of pages | Up to 80-100 pages |
| Print type | Double-sided colour offset printing |
| Additional work | Trimmed to format, paperback |
| Quantity | 8,500 pcs |

| IPARD Leaflets |  |
| --- | --- |
| Dimensions/format | Extended A4 |
| Paper type | Paper 150-200 g/m2 |
| Print type | Double-sided colour offset printing |
| Additional work | Trimmed to format, accordion three, form three bends |
| Quantity | 5,000 pcs |

| IPARD Brochures |  |
| --- | --- |
| Dimensions/format | 160x230mm |
| Cover page | 250-300g/m2 fine art paper (kunstdruk), matte lamination 1/0 |
| Inner paper | Paper 150-200g/m2 |
| Number of pages | Up to 30 pages |
| Print type | Double-sided colour offset printing |
| Additional work | Trimmed to size, saddle stitch bind |
| Quantity | 3,000 pcs |

| Printing/coping the documents |  |
| --- | --- |
| Dimensions/format | A4 |
| Colour | Colour |
| Inner paper | Paper 80-100 g/m2 |
| Print type | Double-sided colour printing |
| Additional work | Saddle stitch bind |
| Quantity | 10,000 pcs |

The Contracting Authority delivers to the selected contractor the text proposal for printed material in Word format (by e-mail and/or on USB). The design proposal and preparation for printing is provided by the Contractor. The Contractor shall design and create a graphic solution for the IPARD guides, leaflets, brochures and deliver in PDF format three design proposals each and per Measure to the Contracting Authority via courier service or alternative means. The printed material in subject has to contain   the Union emblem, flag/coat of arms of the Republic of Serbia and the IPARD visual element while the rule of 25% of area coverage is not required, but the specified elements must be clearly visible and appropriate to the size of the subject material or document.

The design and preparation of printed materials should comply with the current guidelines in the Communication and Visibility Guide for EU External Actions: https://international-partnerships.ec.europa.eu/system/files/2023-04/communicating-and-raising-eu-visibility-guidance-for-external-actions-july-2022_en_0.pdf , in which the basics of the visual identity of the EU are prescribed. Additionally, Guidelines for communication, publicity, and visibility for projects funded under IPARD Programmes will be provided by Contracting Authority.

Licensed - legal fonts should be used. Preparation for printing includes picture editing (light and tonal contrast, dynamic range, colour correction, retouching, sharpening, etc.) up to the maximum quality of the edited photos when compared to the originals, creation of tables, graphs, drawings, schemes, maps and others and converting to process colours. According to the valid Communication and Visibility Guide for EU external activities, the typefaces that can be used on the emblem of the European Union are: Arial, Auto, Calibri, Garamond, Trebuchet, Tahoma, Verdana, Ubuntu.

Underline variations and theme fonts are not allowed. The position of the text must not interfere with the emblem of the Union in any way. The size of the font is proportional to the size of the emblem. The colour of the font is blue „reflex blue“, black or white, depending on the background.

Execution of the subject of the contract: successively, depending on the needs/requirements of the Contracting Authority.

The deadline for preparation and design of the proposal is up to 3 to maximum 5 days (determined by the Contracting Authority). Upon receiving the design proposal from the contractor, the Contracting Authority shall, within 3 days, approve the design proposal, or any objections to it.

The Contractor is obliged to respect the objections of the Contracting Authority, has 3 days to submit the final design of the requested material and, with the consent of the Contracting Authority, conduct a test print.

In the case that the test print does not meet the requirements of the Contracting Authority, the Contractor shall print it again (in accordance with the comments submitted by the Contracting Authority).

Deadline for printing of the materials is up to 10 days from the day of obtaining approval from the Contracting Authority for the design and performing a test print.

The Contractor must guarantee the quality of the printed material, while ensuring an identical print in relation to the colours envisioned during the preparation for printing. The control is carried out by the Contracting Authority. In the event of deficiencies/errors during the service provision, contractor must correct them immediately or in the shortest possible time since the deficiency/error is noted. The deadline for deficiencies/errors corrections shall be done within the three working days after receiving an objection on deficiency/error from the Contracting Authority.

The delivery of the printed material is included in the price and is made to the address of the Department for Management of IPARD Programme, Ministry of Agriculture, Forestry and Water Management of the Republic of Serbia (hereinafter: MAFWM), Bulevar kralja Aleksandra 84/upper ground floor, 11000 Belgrade. The printed material shall be packaged so as to prevent their damage or deterioration in transit to their destination. The name and address of the Contracting Authority, the name of the printed material and the quantity has to be indicated on each package.

The Contractor and the Contracting Authority are obliged to keep the final and approved e-versions of the printed material in their archives. The selected Contractor is obliged to submit to the Contracting Authority the complete preparation of the material with all the fonts used in the preparation, tables, pictures, graphs, etc on USB. The complete produced material is the property of the Contracting Authority.

The contract will be implemented until execution, but not longer than 30th September 2024.

The Contracting Authority does not guarantee the specified quantities.

### Geographical area to be covered

Contract shall apply on the territory of the Republic of Serbia, as defined in the IPARD II Programme.

### Target groups

Target groups are: potential IPARD recipients and IPARD recipients, stakeholders, general public, the IPARD Managing Authority and other IPARD entities and related bodies (operating structure, management structure, advisory services, technical bodies), potential Local Action Groups (pLAG’s) and National Rural (Development) Network, as well as EC and other candidate and EU countries.

## Specific work

In order to achieve the results of this project given under point 2.3. the Contractor should produce listed outputs by carrying out the following activities:

Output 1: Prepared, printed, produced, copied, distributed guides for IPARD measures 1,3,4,5 and 7 (outcome 1):

Activity 1.1.  Preparation of design and printing of guides for IPARD measure 1;

Activity 1.2.  Preparation of design and printing of guides for IPARD measure 3;

Activity 1.3.  Preparation of design and printing of guides for IPARD measure 4;

Activity 1.4.  Preparation of design and printing of guides for IPARD measure 5;

Activity 1.5.  Preparation of design and printing of guides for IPARD measures 7.

Output 2: Prepared, printed, produced, copied, distributed leaflets for IPARD measures 1,3 and 7 (outcome 2):

Activity 2.1.  Preparation of design and printing of leaflets for IPARD measure 1;

Activity 2.2.  Preparation of design and printing of leaflets for IPARD measure 3;

Activity 2.3.  Preparation of design and printing of leaflets for IPARD measure 7.

Output 3: Prepared, printed produced, copied, distributed brochures for IPARD measures 1 and 3 (outcome 2):

Activity 3.1.  Preparation of design and printing of brochures for IPARD measure 1;

Activity 3.2.  Preparation of design and printing of brochures for IPARD measure 3.

Output 4: Printed material for MC meetings (outcome 2):

Activity 4.1. Printing/copying of documents for MC meetings.

In carrying out this task, Contractor shall propose timetable of all steps planned for realization description of the assignment. Timetable has to be agreed by Contracting Authority.

In the case the comments are provided by the Contracting Authority, according to description of the assignment the Contractor shall:

- Incorporate the comments on the printed material design and final approval of promo material proposal by Contracting Authority;

- Deliver samples of printed promo material before printing an agreed quantity.

## Project management

### Responsible body

The Managing Authority for IPARD Programme (hereinafter: IPARD MA), Department for Management of IPARD Programme, MAFWM is responsible for the management of this contract.

### Management structure

The Contracting Authority is responsible for implementation of this contract, the efficient use of the allocated resources to the Contractor for achievement of project results, ensuring the conditions for the contract implementation are met, and cooperating with the Contractor in the planning, approving and controlling of the work schedules supporting the Contractor during the assignment or other assistance, if required.

One kick-off meeting at the beginning of the contract will be held to ensure correct understanding of the contract requirements and explain the role and responsibilities, as well as expectations of each party clarify the specific administrative and implementing procedures.

During the contract implementation, meetings will be organized to follow progress of contracted activities based on request of the Contracting Authority or Contractor. When needed, meetings with the Contractor and the Contracting Authority to clarify/overcome all implementation issues /difficulties will be held.

All meetings between the Contractor and the Contracting Authority shall take place at the premises of the Contracting Authority in Belgrade or online if situation will require, with the prior approval of the Contracting Authority. All costs relating to the preparation and participation in these meetings by the Contractor must be taken into account when preparing the tender and should be included in the costs supported by the Contractor and included in the financial offer.

The approach day-to-day work management and description of the means and tools to be put in place to ensure efficient collaboration with the Contracting Authority shall be explained in the organisation and methodology.

The Contracting Authority will identify a Project Manager for the contract with responsibility to ensure efficient and quality use of allocated resources for achievement of contract targets and approves the draft/final report provided by the Contractor as in part 7 of this ToR. The Project Manager will be responsible for liaison with the Contractor for administrative and monitoring checks over the contract execution by the Contractor on a regular basis. Project Manager shall notify its superiors of difficulties or non-performance during contract implementation.

The Project manager will work closely with the Contractor.

### Facilities to be provided by the contracting authority and/or other parties

Not applicable

# LOGISTICS AND TIMING

## Location

The Contractor’s operations will be based in the Republic of Serbia.

## Start date & period of implementation of tasks

The intended start date is April 2024 and the period of implementation of the contract will be until execution, but not longer than 30th September 2024. Please see Articles 19.1 and 19.2 of the special conditions for the actual start date and period of implementation.

# REQUIREMENTS

## Staff

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be approved to work as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

### Key experts

Key experts are not required

### Other experts, support staff & backstopping

Not applicable

## Office accommodation

Not applicable

## Facilities to be provided by the contractor

The contractor shall ensure that experts are adequately supported and equipped. In particular, it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.

## Equipment

No equipment is to be purchased on behalf of the contracting authority / partner country as part of this service contract or transferred to the contracting authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

The contractor will submit the following reports in English and Serbian in one original and one copy:

Draft final report of maximum 15 pages (main text, excluding annexes). This report shall be submitted no later than one month before the end of the period of implementation of tasks.

Final report with the same specifications as the draft final report, incorporating any comments received from the parties on the draft report. The deadline for sending the final report is 7 days after receipt of comments on the draft final report. The report shall contain a sufficiently detailed description of the different options to support an informed decision on given solutions. The detailed analyses underpinning the recommendations will be presented in annexes to the main report. The final report must be provided along with the corresponding invoice.

## Submission and approval of reports

The report referred to above must be submitted to the project manager identified in the contract. The project manager is responsible for approving the reports.

# MONITORING AND EVALUATION

## Definition of indicators

The Project will be monitored in accordance with standard procedures. Project monitoring and evaluation will be based upon assessment of the progress of the delivery of specified project results against their targets, and the achievements of the project objectives.

The project shall be monitored and supervised by the Contracting Authority. The Contracting Authority shall monitor the implementation based on meetings and reports provided by the Contractor.

The Draft final report will undergo a thorough quality assessment by the Contracting Authority.

Monitoring checks may be carried during the implementation of the assignment, based on the following indicators:

- Indicator 1. Indicative timetable of activities;

- Indicator 2. Proposal of printing material design:

- Indicator 2.1. Guides for IPARD measure 1,

- Indicator 2.2. Guides for IPARD measure 3,

- Indicator 2.3. Guides for IPARD measure 4,

- Indicator 2.4. Guides for IPARD measure 5,

- Indicator 2.5. Guides for IPARD measure 7,

- Indicator 2.6. Leaflets for IPARD measure 1

- Indicator 2.7. Leaflets for IPARD measure 3

- Indicator 2.8. Leaflets for IPARD measure 7

- Indicator 2.9. Brochures for IPARD measure 1

- Indicator 2.10. Brochures for IPARD measure 3

- Indicator 2.11. Material for MC meetings.

•   Indicator 3. Final version printed:

- Indicator 3.1. Guides for IPARD measure 1,

- Indicator 3.2. Guides for IPARD measure 3,

- Indicator 3.3. Guides for IPARD measure 4,

- Indicator 3.4. Guides for IPARD measure 5,

- Indicator 3.5. Guides for IPARD measure 7,

- Indicator 3.6. Leaflets for IPARD measure 1

- Indicator 3.7. Leaflets for IPARD measure 3

- Indicator 3.8. Leaflets for IPARD measure 7

- Indicator 3.9. Brochures for IPARD measure 1

- Indicator 3.10. Brochures for IPARD measure 3

- Indicator 3.11. Material for MC meetings.

## Special requirements

All copyrights and intellectual rights over the delivered service are in the unlimited and unconditional ownership of the Contracting Authority.

The Contractor shall permit Contracting Authority, or any person authorised by the Contracting Authority, the IPARD Agency, the NAO, NF, the IPA Audit Authority, the European Commission, the European Court of Auditors or OLAF - the European Anti-Fraud Office - to inspect or audit the records and accounts related to the service and make copies of both during and after provision of the services.

The Contractor must keep all the documents related to the contract implementation for a period of seven years following the closure of the contract.